## Sheet1
Activity |  | Approximate Date | Actual Date
Call to Rector from Chairman | 8-9 Months | 2014-02-04
Indoctrination Meeting with respective Leaders person | 7-8 Months | 2014-04-06
Rector Orientation (Approval of 6 key leaders and professors) | T-27 | 2014-05-01
Key Leaders Training | T-21 | 2014-06-12
Rector Call to Professors | T-18 | 2014-07-03
Team Selection Meeting (May be after preceding weekend based on weekend dates) | T-16 | 2014-07-17
Professors Meeting (May be before preceding weekend based on weekend dates, Leaders person will direct) | T-16 | 2014-07-17
Heads Meetings (Must be after preceding weekend) | T-16 | 2014-07-17
First of 8 Team Meetings (meetings may be combined) | T-9 | 2014-09-11
Weekend (Fill in the weekend date like 11/6/08, the other dates will calculate) | T = 0 | 2014-11-06
Debrief Meeting | T+2 | 2014-11-20
Formulas:
Approximate Date = [Approximate Date, row below]-56
Approximate Date = [Approximate Date, row above]+14